## Slide 1
[Project_Name] KICK OFF MEETING
Date:

## Slide 2
Overview
Scope of Work and Allocation to Teams
Project Delivery Milestones
Project Team Members and Roles
Milestone Deliverables
Project Deliverables and Tracking Tools
Project Tools
Communication Plan
Immediate Actions in the Next Few Weeks
Pitfalls in Phase 1 and Lessons Learned
Risks at Project Start
Questions
AGENDA

## Slide 3
AGENDA
Project Overview
1
Project Scopes
2
Deliverables & Milestones
3
Project Critical Dependencies
4
Risk/Issue
5
Communication plan
6
Open Discussion
7

## Slide 4
Project ID:
Project Name:
Planed start date:
Planed end date:
Hub:
Client:
Plan Effort (PersonDays):
Additional information: NA
1.1 Project Summary
1. PROJECT OVERVIEW
1.2 Project short description

## Slide 5
Scope of Work and Allocation to Teams (part 1 of 2)
2. PROJECT SCOPES
Work Package | Brief Description | Team Responsible
CAN-FD | -SRS and SAD creation -Tranceiver driver development | RBVH
 | -SRS and SAD creation -Bootloader enhancement to use CAN-FD for reflashing | RBEI
Ethernet BroadR-Reach | -SRS and SAD creation -Driver development -CUBAS Ethernet stack integration -Compliance to BroadR-Reach standard | RBVH
LIN J2602 | -SRS and SAD creation -RTA-LIN integration | RBVH
 | -ISOLAR A support for J2602 and NCF | ISOLAR-A Team
SENT SRS | -SRS and SAD creation | RBVH
RS485 SRS | -SRS and SAD creation | RBVH
FlexRay | -SRS and SAD creation -RTA-Flexray stack integration | RBVH

## Slide 6
Scope of Work and Allocation to Teams (part 2 of 2)
NEXTecu Phase 2
Project Kick-off
Work Package | Brief Description | Team Responsible
D2A | -SRS creation -D2A Driver development | Hycon
SD-ADC | -SRS creation -SD-ADC Driver development | Hycon
Constant Current Driver (CCD) | -SRS creation -CCD Driver development | Hycon
Secondary Safety MCU | -SRS creation -SSM development | Hycon
Multicore Capability (MC) | -SRS creation -convertion to MC | to be confirmed.
Note: Integration Plan to be created will define the number of times integration between teams will be needed.

## Slide 7
Project Delivery Milestones
NEXTecu Phase 2
Project Kick-off
Delivery Milestone | Description | Date
SRS for Phase 2 Delivery 1 | Release of SRS and SAD documents for CAN-FD, D2A, and SD-ADC software | 29 Jul 2016
Phase 2 Delivery 1 (P2D1) | Release of CAN-FD, D2A, and SD-ADC software | 31 Aug 2016
SRS for Phase 2 Delivery 2 | Release of SRS and SAD documents for Ethernet, FlexRay, and SENT software | 12 Sep 2016
Phase 2 Delivery 2 (P2D2) | Release of Ethernet and FlexRay software | 30 Sep 2016
SRS for Phase 2 Delivery 3 | Release of SRS and SAD documents for LIN, Multicore, CCD, and RS485 software | 10 Oct 2016
Phase 2 Delivery 3 (P2D3) | Release of LIN, Multicore, and CCD software | 31 Oct 2016
SRS for Phase 2 Delivery 4 | Release of SRS and SAD for Secondary Safety Microcontroller software | 11 Nov 2016
Phase 2 Delivery 4 (P2D4) | Release of Secondary Safety Microcontroller software | 30 Jan 2017

## Slide 8
Project Team Members and Roles
NEXTecu Phase 2
Project Kick-off
Role | Name
Project Manager | Ramos Dennis (ETAS/EES3)
Hub Technical Support – ETAS-Ana | to be confirmed
Lead Architect | Phan Thanh Hoang (RBVH/ESS4)
Project Lead - RBVH | Phan Thanh Hoang (RBVH/ESS4)
Configuration Manager | Ramos Dennis (ETAS/EES3)
Software Integrator | Phan Thanh Hoang (RBVH/ESS4)
Test Manager | to be confirmed
PPQA | Nguyen Thi Cam Van (RBVH/ESS)
RBVH Developers | Nguyen Hoai Nam (RBVH/ESS4) Tran Van Truong (RBVH/ESS4) Le Quang Long (RBVH/ESS4) to be confirmed
Hycon Point of Contact | Parker Mosman (email: parker.mosman@hyconinc.com )
ISOLAR-A Team Point of Contact | Reckels Bernhard (ETAS-PGA/PRM-E)
RBEI EBB Point of Contact | Sushamshushekar Doddabasappa (RBEI/EBB3)

## Slide 9
Milestone Deliverables (Part 1 of 2 – done from Requirements Phase to Release Phase for every work package)
NEXTecu Phase 2
Project Kick-off
Deliverables | Delivered to ETAS? | Delivered to TACOM? | Responsible for Delivery
Updated SRS | Yes | Yes | Dev’t Team
Updated SAD | Yes | Yes | Dev’t Team
MRS and DD | Yes | No | Dev’t Team
Unit Test Report | Yes | No | Dev’t Team
Source Code, Configuration, Scripts, and Build Files | Yes | Yes | Dev’t Team
Software Build | Yes | Yes | Dev’t Team
Release Notes | Yes | Yes | Dev’t Team
Integration Test Report | Yes | No | Dev’t Team
Updated User Manual | Yes | Yes | Dev’t Team
OSS Scan Report | Yes | No | Dev’t Team
Release Readiness Review Report | Yes | No | Dev’t Team
*Only Updated SRS and SRD are applicable to SENT and RS485

## Slide 10
Milestone Deliverables (Part 2 of 2)
NEXTecu Phase 2
Project Kick-off
Deliverables | Delivered to ETAS? | Delivered to TACOM? | Responsible for Delivery
System Test Report | Yes | Yes | Test Team
Updated Automatic Test System Design | Yes | No | Test Team
RT2 Files and Scripts | Yes | No | Test Team
Updated Traceability Matrix | Yes | No | Test Team
Acceptance Test Specification | NA | No | Hub Technical Support
Baseline Audit Report | NA | No | Configuration Manager
Updated Lessons Learned | NA | No | Project Manager

## Slide 11
Project Deliverables (done once at start of project)
NEXTecu Phase 2
Project Kick-off
Deliverables | Role Responsible
Project Management Plan | Project Manager
MS Project Plan | Project Manager
Configuration Management Plan | CM Manager
Integration Plan | Lead Architect
Test Strategy and Plan | Test Manager
Project Tracking Tools
Tracked subject | Tools
Effort and Progress | MS Project
Minutes of Meetings | OIL
Risk Management | OIL
Project/Technical Issues Tracking | JIRA
Change Management (Defect and CR) | JIRA
Tool Management | Tools Tracker (Excel)

## Slide 12
Communication Plan
NEXTecu Phase 2
Project Kick-off
Meetings | Frequency | Days and Time
Project Status | Weekly | Thursdays (0800H or 1800H alternating)
CCB Level 1 (Project Team Level) | Yes | Tuesdays
CCB Level 2 (Business and Program Management) | Yes | Wednesdays
Technical Meetings | NA (As needed) | NA (As needed)
*Note: CCB Level 2 includes Oliver Korasiak (Hub Business Manager) and Jamey Cates (Hub Program Manager)

## Slide 13
Release detailed and baseline Microsoft Project Plan
Establish SVN repository for project documents
Establish JIRA for all tracking
Prepare for “One-roof” meeting
Immediate actions in the next few weeks
NEXTecu Phase 2
Project Kick-off

## Slide 14
Transparency into RBEI-EBA who was initially allocated the drivers was not established. LL: Plan closely with the team and require details.
Impact analysis on change from RBEI-EBA to RBVH was not thoroughly considered. The only basis was effort estimation that did not include Lambda development. LL: Change Process with CCB needs to be applied for this type of project change.
MPP baseline from allocated team came too late. LL: Single MPP managed by Hub Project Manager
Using multiple MPP made tracking unreliable and required separate effort reports. LL: Single MPP to be used by all teams.
Too many OIL caused some issues to remain unresolved. LL: Use JIRA which can centralize all issues.
When faced with technical issues (e.g. Lambda) that block activities, assigned resource becomes idle. Overspend is the result of maintaining the idle resource on the project. LL: Project Steering Committee to decide based on recommendation of project manager and resource manager.
Pitfalls from Phase 1 and corresponding Lessons Learned.
NEXTecu Phase 2
Project Kick-off

## Slide 15
Risks at Project Start
NEXTecu Phase 2
Project Kick-off
Wrong assumption in estimation | If current assumption of "all customer requirement shall be covered by CUBAS Eth stack" is wrong, then Risk for HUGE gap in actual effort may occur, which impact to project cost and schedule
Technical blocker | If there is no alternative for technical expert from ETAS to cover the Phase 2, then Risk for technical blocker happens (just like Lambda), which impacts to the delay or even incompletion of project
Hardware blocker | If Ethernet communication interface arrive to RBVH later than Aug, then risk to delay of Implementation and Testing for this work package, which Impacts to the delay of project
Multicore responsible resource delayed | If resource is not assigned to Multicore on time, P2D3 will be delayed which impacts to ETAS revenue this year.
Test Manager resource delayed | If resource is not assigned to manage, develop, and execute testing on time, System Testing will be delayed which impacts to the Phase 2 schedule.
Hub Technical Support resource delayed | If resource is not available in Ann Arbor, there will be no one to do Acceptance Test and Final Reviews, which impacts to Phase 2 schedule.
Hub Technical support resource delayed (for ANA integration) | If resource is not available in Ann Arbor, there will be no one to do integration of Hycon to RBVH deliveries, which impacts to schedule.

## Slide 16
QUESTIONS?
NEXTecu Phase 2
Project Kick-off